## Sprint Backlog
Story | Sprint Backlog Item | Task | Task Details | Initial Effort (hrs) | Day 1 Remaining | Day 2 Remaining | Day 3 Remaining | Status
US01 | User Registration | Registration API | Create user account with validation | 6 | 3 | 1 | 0 | Done
US02 | User Login | Login API | Authentication and session management | 5 | 3 | 1 | 0 | Done
US03 | Profile Management | Update Profile | Edit personal details | 4 | 2 | 1 | 0 | Done
US04 | Ride Search | Search Ride | Search rides | 6 | 4 | 2 | 0 | Done
US05 | Book Ride | Booking API | Reserve seat | 8 | 6 | 3 | 0 | Done
US06 | Cancel Ride | Cancel Booking | Cancel booked ride | 4 | 3 | 1 | 0 | Done
US07 | Ride History | View History | View ride history | 5 | 3 | 1 | 0 | Done
US08 | Driver Registration | Driver Signup | Register driver | 6 | 4 | 2 | 0 | Done
US09 | Add Vehicle | Vehicle API | Add vehicle | 5 | 3 | 1 | 0 | Done
US10 | Create Ride | Publish Ride | Publish ride | 7 | 5 | 2 | 0 | Done
US11 | Edit Ride | Update Ride | Update ride | 4 | 2 | 1 | 0 | Done
US12 | Delete Ride | Remove Ride | Delete ride | 3 | 2 | 1 | 0 | Done
US13 | Accept Passenger | Approval | Accept request | 5 | 3 | 1 | 0 | Done
US14 | Reject Passenger | Rejection | Reject request | 3 | 2 | 1 | 0 | Done
US15 | Payment | Payment Module | Online payment | 8 | 6 | 3 | 0 | Done
US16 | Payment History | Transactions | Payment records | 5 | 3 | 1 | 0 | Done
US17 | Ratings | Rating System | Rate driver | 4 | 2 | 1 | 0 | Done
US18 | Notifications | Notification Service | Ride alerts | 5 | 3 | 1 | 0 | Done
US19 | Admin Dashboard | Dashboard | Monitor system | 6 | 4 | 2 | 0 | Done
US20 | Reports | Reports Module | Generate reports | 6 | 4 | 2 | 0 | Done