## Sprint Backlog
Story | Sprint Backlog Item | Task | Task Details | Volunteer | Initial Effort (hrs) | Day 1 Remaining | Day 2 Remaining | Day 3 Remaining | Day 4 Remaining | Status
US01 | Role-based Login | UI Design | Dessign login screen for Admin,Driver,Passenger |  | 6 | 3 | 1 | 0 |  | Done
US02 | Driver Creation | Develop API | Create driver account with validations and Driver ID generation |  | 5 | 3 | 1 | 0 |  | Done
US03 | View Registered Drivers | Driver List | Display registered drivers with search and filter options |  | 4 | 2 | 1 | 0 |  | Done
US04 | Terminate Drivers | Update Status | Terminate driver account and record reason |  | 6 | 4 | 2 | 0 |  | Done
US05 | View Registered Passengers | Passenger List | Display passenger records with filtering |  | 8 | 6 | 3 | 0 |  | Done
US06 | Ride Approval | Approval Process | Approve or reject ride requests submitted by drivers |  | 4 | 3 | 1 | 0 |  | Done
US07 | Admin Activity Audit Trail | Activity Log | Record admin activities and generate audit reports |  | 5 | 3 | 1 | 0 |  | Done
US08 | Driver Registration | Registration | Register driver and validate input details |  | 6 | 4 | 2 | 0 |  | Done
US09 | Create Ride | Ride Creation | Create ride with pickup,drop,fare and timing details |  | 5 | 3 | 1 | 0 |  | Done
US10 | View all Rides | Ride Display | Display available rides with sorting options |  | 7 | 5 | 2 | 0 |  | Done
US11 | Edit Ride Details | Ride Update | Modify ride details using race_id in the system |  | 4 | 2 | 1 | 0 |  | Done
US12 | Cancel Ride | Ride Cancellation | Cancel ride and update ride availability |  | 3 | 2 | 1 | 0 |  | Done
US13 | Update Driver Profile | Profile Update | Edit driver personal and vehicle information |  | 5 | 3 | 1 | 0 |  | Done
US14 | Passenger Registration | Registration for Passenger | Register Passenger with required validations |  | 3 | 2 | 1 | 0 |  | Done
US15 | Browse Ride | Search Ride | Search rides using source and destination |  | 8 | 6 | 3 | 0 |  | Done
US16 | Book a Ride | Ride Booking | Book ride and ride detials should be displayed in Bookings History |  | 5 | 3 | 1 | 0 |  | Done
US17 | Rate Driver | Rating | Submit driver rating after ride completion |  | 4 | 2 | 1 | 0 |  | Done
US18 | Update Passenger Profile | Profile Update | Update passenger personal information |  | 5 | 3 | 1 | 0 |  | Done
US19 | Deactivate Passenger Account | Account Deactivation | Disable passenger account and restrict login |  | 6 | 4 | 2 | 0 |  | Done
US20 | Logout | Logout from the system | End user session and redirect to Login Page |  | 6 | 4 | 2 | 0 |  | Done